## Slide 1
TECHNICAL & FINANCIAL PROPOSAL
MaHIS–iCHIS Integration for
Maternal & Newborn Health
Technical Architecture & Costed Roadmap · ACHIEVE Project · Malawi
Last Mile Health × Ministry of Health & Sanitation
Lilongwe · August 2026

## Slide 2
CONTEXT
The ACHIEVE Project
Digital Health Consultant Proposal · 1
What ACHIEVE is
US Department of State–funded initiative implemented by Pact and partners to accelerate sustainable reductions in maternal, neonatal and child mortality across pregnancy, childbirth, postnatal and early childhood services.
Where it works
Karonga, Balaka, Thyolo and Zomba districts. Last Mile Health leads the design and implementation of iCHIS-driven interventions in Balaka district.
Objective 3 — system strengthening
Strengthening emergency referral systems, commodity management and supply chain, enhanced use of data for decision-making, and preparedness for public health emergencies.
LMH Strategic Objectives
SO1: Enhance iCHIS functionality and develop the architecture and costed roadmap for MaHIS–iCHIS integration for improved MNH outcomes. SO2: Build CHW capacity in Balaka on iCHIS and community-based maternal & neonatal care (CBMNC).

## Slide 3
THE CHALLENGE
Two Systems, One Continuum of Care — Not Yet Connected
Digital Health Consultant Proposal · 2
MaHIS captures facility data; iCHIS captures community data — parallel worlds today.
Duplicate entry of MNH service data into national reporting.
Manual reconciliation delays reports and degrades quality.
Referrals between HSAs and facilities are rarely tracked to closure.
Decision-makers lack visibility of the full continuum of MNH care.
iCHIS
Community level — HSAs / CHWs
MaHIS
Facility / HMIS
GAP
Delayed, duplicated MNH reporting · weak referral closure · weak decisions
Integration closes this gap — one trusted flow of MNH data.

## Slide 4
SCOPE
Understanding of the Assignment
Digital Health Consultant Proposal · 3
Systems
MaHIS (facility / HMIS) ↔ iCHIS (community), with DHIS2 as the national analytics backbone
Data domains
CHW registrations · service delivery data · stock / commodity data · priority MNH indicators
Use cases
Automatic submission of CHW monthly summaries into HMIS · two-way referral tracking · consolidated MNH dashboards
Standards frame
National digital health architecture & governance standards; HL7 FHIR, OpenHIE profiles, DHIS2 data model
Constraints
~6.5-week window · USD 3,000–4,000/month fee band · co-location in Lilongwe · Malawian national consultant

## Slide 5
APPROACH
From Discovery to Donor-Ready Package in Five Steps
Digital Health Consultant Proposal · 4
01
Discovery
Document review · 8–10 interviews · 2 district site visits · vendor sessions
Output: Validated current-state assessment
02
Architecture design
Pattern options analysis · selection workshop with MoH interoperability team
Output: Endorsed integration architecture
03
Requirements engineering
FR/NFR workshops · data-mapping matrix · OpenAPI 3.0 draft · security review
Output: Technical requirements document
04
Roadmap & costing
Four-phase plan · People / Platforms / Process / TTV pillars · donor mapping
Output: Costed implementation roadmap
05
Risk & consolidation
P×I risk workshop · mitigation planning · executive summary · deck assembly
Output: Final package + presentation
Government-first · Standards-based (FHIR / OpenHIE) · Evidence-led · Cost honesty · Donor-ready outputs

## Slide 6
INDICATIVE ARCHITECTURE
A Standards-Based Interoperability Layer
Digital Health Consultant Proposal · 5
iCHIS
Community level — HSAs / CHWs
Interoperability layer
OpenHIM + FHIR APIs (OpenHIE-aligned)
MaHIS
Facility / HMIS
DHIS2
National analytics & dashboards
OAuth2 · TLS encryption · audit logging
Starting hypothesis — confirmed or revised in Weeks 3–4 against vendor capability, infrastructure and governance findings. File-based exchange documented as fallback.

## Slide 7
DELIVERABLES
Five Decision-Grade Products
Digital Health Consultant Proposal · 6
D1
Inception Report
End Week 2
Scope, RACI & workplan signed off; ≥10 risks logged; repository live.
D2
Technical Architecture & Requirements
End Week 4
Validated current state; ≥30 FRs, ≥15 measurable NFRs; OpenAPI draft; compliance matrix.
CORE PRODUCT
D3
Costed Implementation Roadmap
End Week 6
Four phases with gates; monthly costing by pillar; CAPEX/OPEX split; donor matrix.
D4
Risk Analysis & Mitigation Plan
Week 7
≥20 risks across four categories; every High/Medium risk owned with trigger.
D5
Final Package & Presentation
30 Sep
Executive summary ≤2 pages; annexes; 20-slide donor deck; formal sign-off.

## Slide 8
CORE PRODUCT
The Costed Implementation Roadmap
Digital Health Consultant Proposal · 7
Four phases
Phase 0 · Preparation & Governance
Alignment, working group, data-sharing agreements
Months 1–2
Phase 1 · Design & Prototyping
Data mapping, limited-site pilot build, testing
Months 3–5
Phase 2 · Pilot Rollout
District deployment, training, monitoring & refinement
Months 6–11
Phase 3 · Scale-Up & Institutionalisation
National rollout, SOPs, handover to MoH
Months 12–18+
People
Integration architect, developers, data engineer, PM & M&E, trainers, TWG coordination — person-months × local rates
Platforms
Middleware / API management licences, hosting & storage, security tooling, maintenance retainers
Process
Mapping & terminology harmonisation, QA environments, legal & DSA reviews, documentation, change management
Time-to-Value
Efficiency narrative — reduced duplication, faster reporting — and the quantified cost of delay if integration stalls
Monthly granularity · CAPEX/OPEX split · 15% contingency · benchmarked vs regional projects · mapped to Global Fund / USAID / Gavi windows

## Slide 9
IMPLEMENTATION ROADMAP
Phased Path to National Scale
Digital Health Consultant Proposal · 8
Phase 0 · Preparation & Governance
Months 1–2
• Stakeholder alignment
• Technical working group established
• Data-sharing agreements drafted
Gate: governance endorsed
Phase 1 · Design & Prototyping
Months 3–5
• Detailed data mapping
• Limited-site pilot development
• Initial testing & validation
Gate: pilot ready
Phase 2 · Pilot Rollout
Months 6–11
• Deploy in selected districts/facilities
• Train users & technical staff
• Monitor, troubleshoot, refine
Gate: go/no-go to scale
Phase 3 · Scale-Up & Institutionalisation
Months 12–18+
• National / multi-region rollout
• SOPs, job aids, routine operations
• Handover to government
Gate: sustainable handover
Durations indicative — validated and re-baselined during Weeks 5–6 of the consultancy.

## Slide 10
WORK PLAN
Six and a Half Weeks, Seven Checkpoints
Digital Health Consultant Proposal · 9
W1–2 · Inception & Discovery
Kick-off · interviews · 2 district visits · discovery synthesis
CP1 baseline · CP2 discovery validation
W3–4 · Architecture & Requirements
Pattern selection · FR/NFR workshops · data mapping · API spec draft · clinical validation
CP3 architecture review · CP4 requirements sign-off
W5–6 · Roadmap & Costing
Phasing · four-pillar costing model · donor alignment · validation workshop
CP5 roadmap sign-off
W7 · Risk & Close
Risk workshop · package assembly · final review · handover
CP6 package review · CP7 formal acceptance
Cadence & quality: daily stand-up · weekly written status report (Fri) · bi-weekly steering committee · version control v0.x → v1.0 FINAL · peer review before every formal submission

## Slide 11
GOVERNANCE & STAKEHOLDERS
Co-Located With the Decision-Makers
Digital Health Consultant Proposal · 10
Engagement governance
REPORTING LINE
Digital Health Specialist, Last Mile Health — with close technical coordination with the Head, Systems Architecture & Security Unit, MoH Digital Health Division
CADENCE
Daily stand-up · weekly status report · bi-weekly steering committee
QUALITY
Seven checkpoints (CP1–CP7) with go/no-go criteria; traceability from requirements → architecture → roadmap → cost → risk
CHANGE CONTROL
Scope changes only through steering-committee impact assessment
Stakeholders engaged weekly
MoH Digital Health Division
Reproductive Health Unit
District DHMTs (pilot districts)
HSAs & CHWs
Development partners — Global Fund, USAID, Gavi, UNICEF
System vendors — iCHIS (Baobab) & MaHIS
LMH country & technical teams

## Slide 12
RISK MANAGEMENT
Named Risks, Owned Mitigations — Reviewed Weekly
Digital Health Consultant Proposal · 11
MoH staff availability constrained by competing priorities
HIGH
Pre-booked calendars; sponsor escalation; flexible scheduling
Vendor API access or sandbox delayed
MED–HIGH
Early MoH directive to vendors; contractual clauses; file-exchange fallback
Scope creep beyond the MNH integration core
MEDIUM
Inception baseline; formal change-control board
Donor funding misaligned with phased roadmap
MED–HIGH
Donor mapping in Week 6; modular phasing enables partial funding
Existing data quality undermines integration value
HIGH
Data-quality assessment in discovery; cleansing sprint budgeted in Phase 1
Security/compliance gaps block future deployment
LOW × CRITICAL
Early MoH ICT security review; privacy-by-design; DPA templates ready

## Slide 13
INVESTMENT CASE
Transparent Fees, Realistic Reimbursables
Digital Health Consultant Proposal · 12
Professional fees
USD 3,500 per month
Within the advertised USD 3,000–4,000 band.
≈ USD 5,400 total professional fees across the 6.5-week engagement.
Excludes withholding taxes per applicable law.
Indicative reimbursables (USD)
Local travel — 2 district visits
400
Workshops (venue, refreshments × 4)
300
Communications / internet
150
Printing & stationery
100
Contingency (~10%)
635
Total estimated engagement
6,985
One roadmap, multiple funding doors — formatted for Global Fund RSSH, USAID Digital Health, Gavi HSS and World Bank concept notes.

## Slide 14
QUALIFICATIONS
Built for This Exact Brief
Digital Health Consultant Proposal · 13
Progressive LMIC experience designing and costing digital-health system integrations
Hands-on with national HIS platforms — DHIS2, OpenMRS, CommCare/ODK, iCHIS-class tools
Working command of interoperability standards — HL7 FHIR, OpenHIE, API design
Data-governance track record — data-sharing agreements, privacy and security compliance
Costing prepared for Global Fund, USAID, Gavi and World Bank audiences
Facilitated multi-stakeholder MoH consultations to consensus
Translates technical concepts for non-technical audiences
Excellent English; based in Lilongwe for full-time co-location
Differentiator: familiarity with Malawi's digital-health ecosystem and Ministry of Health digital-health priorities.

## Slide 15
SUSTAINABILITY
Handover Is the Deliverable
Digital Health Consultant Proposal · 14
Handover pack
✓ Editable sources — Word, Excel, PowerPoint
✓ Costing model with assumptions tab (unlocked)
✓ Living risk register with owners and triggers
✓ OpenAPI specs and data-mapping matrices
✓ Decision register and meeting logs
Mechanisms that outlast the consultancy
✓ MoH ownership board — quarterly steering
✓ Technical working group — monthly coordination
✓ Recurrent budget-absorption tracking (Phase 1 onward)
✓ Vendor SLAs embedded in Phase-1 contracts
✓ Annual roadmap review and refresh
Success test: the MoH lead can present the roadmap accurately — without the consultant in the room.

## Slide 16
NEXT STEPS
Ready to Start Within Days of Signature
1
Approve proposal and countersign the engagement letter
2
Confirm MoH workspace access, badging and stakeholder calendars (Week −1)
3
Kick-off meeting with LMH and the MoH Digital Health Division
4
First deliverable draft — Inception Report — by end of Week 2
[Consultant Name] · Lilongwe, Malawi · [email address]