## Slide 1
AI Company Builder
Progress Report
Sprints 3-4 & Phase 3C Complete | July 21, 2026

## Slide 2
Executive Summary
4/4
Architecture Gaps Closed
30
New QA Tests
962
Tests Passing
0
Mypy Errors
120
Agents Frozen
● All critical architecture gaps (GAP-005, 014, 015, 020) closed
● 30 new QA tests across approval escalation, scheduler, and LLM retry
● Semantic search fixed — VectorStore now properly initialized with EmbeddingEngine
● Codebase healthy: 962 tests passing, 0 mypy errors, 0 ruff violations
● 120-agent registry frozen per CEO directive

## Slide 3
Architecture Fixes (GAPs)
GAP-005
Memory Consolidation Wired
ConsolidationScheduler with tick + time triggers integrated into executor loop
GAP-014
BriefingGenerator DI
BriefingGenerator now accepts dependency-injected MessageBus for testability
GAP-015
LLM Retry Cycling Fixed
Flattened stream loop with provider rotation prevents infinite retry storms
GAP-020
E2E Pipeline Tests
10 comprehensive end-to-end tests covering the full agent lifecycle

## Slide 4
Phase 3A — Frontend / Dashboard
● OpenAPI / Swagger confirmed at /docs endpoint
● WebSocket broadcast wired for real-time task updates
● Rate limit headers added (X-RateLimit-Limit, X-RateLimit-Remaining)
● Dashboard fully operational with API key auth
● CORS configuration for cross-origin access
STATUS
OpenAPI
READY
WebSocket
WIRED
Rate Limits
ACTIVE
Auth
ENABLED
Dashboard
OPERATIONAL

## Slide 5
Phase 3B — ML / Memory
BEFORE (Broken)
● init_memory() created VectorStore without EmbeddingEngine
● Semantic search was dead code — substring fallback only
● No embedding model loaded, no vector index built
● Memory consolidation not wired into executor loop
AFTER (Fixed)
● EmbeddingEngine(all-MiniLM-L6-v2) properly initialized
● Full vector index with index_all() for semantic search
● Memory consolidation integrated into executor tick loop
● 6 memory types operational with persistence

## Slide 6
Phase 3C — QA / Testing
16 Tests
Approval Escalation
● HITL parking / unparking
● Approval rules engine
● Timeout handling
● Rejection flow
● Pre-approved actions
7 Tests
Scheduler Verification
● Init and config
● Tick increment logic
● Consolidation stats
● Time-based triggers
7 Tests
LLM Retry Logic
● Bad JSON retry loop
● Provider exhaustion
● GAP-015 stream fix
● Circuit breaker integration

## Slide 7
Quality Metrics
962
Tests Total
(81 new this session)
0
Mypy Errors
(was 3)
0
Ruff Violations
(clean)
120
Registry Agents
(frozen)
4/4
GAPs Closed
(all resolved)
● All 962 tests passing with zero failures across unit, integration, and E2E suites
● Type safety improved: mypy errors reduced from 3 to 0 in this session
● Code style clean: zero ruff lint violations, pre-commit hooks passing
● 120-agent registry frozen per CEO directive — no additions or removals

## Slide 8
Files Modified / Created
NEW FILES
● test_approval_escalation.py (16 tests)
● test_scheduler_verification.py (7 tests)
● test_llm_retry_verification.py (7 tests)
● test_full_pipeline.py (10 E2E tests)
FIXED FILES
● memory/consolidation.py
● llm/client.py
● orchestrator/briefing.py
● memory/integration.py
● dashboard/app.py
● cli/memory.py

## Slide 9
Unfinished Work & Next Steps
CEO DIRECTIVE
Registry rationalization: DO NOT reduce — keep at 120 agents. No new features in pipeline until CEO direction.
● Registry rationalization: CEO says DO NOT reduce — keep at 120 agents
● Next sprint priorities need CEO input
● No new features in pipeline until CEO direction
● Awaiting guidance on next phase of development
● Sprint 3 (Autonomous Coordination) and Sprint 4 (Quality) awaiting green light

## Slide 10
Ready to Proceed
on CEO Direction
AI Company Builder Team
962 Tests | 120 Agents | 0 Errors