## Slide 1
VillageReach
CHOICE Project – USSD Health Messaging Consultant
Financial Proposal & Technical Approach
Prepared by Light Speed Holdings | September 2026 | Last updated: 2026-09-18
Malawi · Nairobi · Washington DC
Confidential – For VillageReach Evaluation Use Only

## Slide 2
Agenda
01
Executive Summary & Value Proposition
02
Understanding of Requirements
03
Technical Approach & USSD Architecture
04
Team Composition
05
Project Timeline & Milestones
06
Budget & Financial Proposal
07
Data Privacy & Security
08
Next Steps

## Slide 3
Executive Summary
The Engagement
• USSD health messaging service on short code 54747
• TNM and Airtel networks in Malawi
• Chichewa-language content for women in Balaka & Lilongwe
• 4-week technical setup + 24-month maintenance
• CHOICE Project (Global Affairs Canada / Oxfam Canada)
Why Light Speed Holdings
• Proven USSD & mobile health deployments in Malawi
• Full-stack team: developers, UX researchers, integration engineers
• Local Malawi presence with international standards
• Single accountable partner—no subcontracting
• Value for money: milestone-based payments

## Slide 4
Understanding of Requirements
Core Deliverables
USSD Menu Design & Deploy
Short code 54747 (TNM + Airtel) Chichewa-language menus ≤182 chars/screen, ≤4 levels deep
User Acceptance Testing
Minimum 20 participants Balaka & Lilongwe districts Low-literacy user validation
Data Pipeline Integration
REST API to VillageReach systems Monthly uptime & usage reports ≥99% availability target
Training & Handover
Documentation for VillageReach staff 24-month support commitment Completion report at engagement end

## Slide 5
Technical Approach – 4-Phase Methodology
Phase 1
Discovery & Design
Week 1
Stakeholder interviews Content architecture Wireframe development Technical architecture
Phase 2
Build & Test
Weeks 2–3
USSD application dev REST API implementation Internal QA Performance testing
Phase 3
UAT & Launch
Week 4
UAT with 20+ users Iterative refinement Production deployment Go-live monitoring
Phase 4
Maintain & Report
Months 2–24
Monthly reports Content updates Bug fixes & optimization Completion report

## Slide 6
USSD Menu Wireframe – Short Code 54747
Main Menu
Welcome to CHOICE 1. Thanzi la thanzi 2. Kukhala ndi moyo 3. Ubwenzi bwino 4. Zambiri 99. Main Menu
1. Thanzi la thanzi
Thanzi la thanzi 1. Thanzi la amai 2. Thanzi la ana 3. Matenda osowa 4. Mphamvu ya chakudya 99. Main Menu
1.1 Thanzi la amai
Kukhala ndi moyo wa thanzi: • Kusamba pochapa • Kudya zakudya zoyenera • Kuchita masewera 99. Main Menu
→
→
All screens: ≤182 characters | Number-driven navigation | "99. Main Menu" on every screen | ≤4 levels deep

## Slide 7
Team Composition
Consulting Lead
Jmlus
Project management Malawi health sector
Allocation: 30%
Solution Architect
Senior Backend
USSD gateway integrations REST API design
Allocation: 25%
Mobile Developer
USSD Specialist
USSD app development Chichewa systems
Allocation: 40%
Integration Engineer
API Specialist
REST API pipelines Data quality
Allocation: 20%
UX Research Lead
Low-Literacy UX
User research Malawi Interface design
Allocation: 15%
Data Privacy Officer
Compliance
GDPR/NDPR Health data protection
Allocation: 10%
QA Engineer
Test Lead
USSD testing UAT coordination
Allocation: 20%
Financial Analyst
Budget Lead
NGO budgeting USD/MWK forecasting
Allocation: 5%
Document Designer
Deliverables
Reports & documentation Training materials
Allocation: 10%
Business Developer
Client Relations
VillageReach management Stakeholder coordination
Allocation: 5%

## Slide 8
Project Timeline – 24 Months
Phase 1
Discovery & Design
Week 1
Phase 2
Build & Test
Weeks 2–3
Phase 3
UAT & Launch
Week 4
Phase 4
Maintain & Report
Months 2–24
Key Milestones
Contract Signing
Day 0
40% payment
Wireframes Approved
End of Week 1
—
USSD Build Complete
End of Week 3
—
Go-Live on 54747
End of Week 4
20% payment
Monthly Reports
Months 1–24
40% in monthly installments
Engagement Complete
Month 24
—

## Slide 9
Budget & Financial Proposal
Phase 1: Setup
$13,350
4 weeks USSD design & development UAT & launch Documentation
Phase 2: Maintenance
$25,633
24 months Monthly reporting Content updates Bug fixes & optimization
Reimbursables
$1,926
Travel & logistics Testing SIMs UAT participant incentives
TOTAL ENGAGEMENT VALUE
$45,000
Incl. 10% contingency ($4,091)
≈ $1,875/mo all-in
Payment: 40% signing | 20% go-live | 40% monthly

## Slide 10
Payment Schedule
Payment 1
Contract Signing
Day 0
$18,000
40%
Payment 2
Go-Live
End of Week 4
$9,000
20%
Payments 3–26
Monthly Maintenance
Months 1–24
$750/mo
40% (× 24)

## Slide 11
Data Privacy & Security
Data Minimization
USSD collects only minimum required data; no PII stored unless authorized
Encryption
TLS 1.3 in transit; AES-256 at rest; OAuth 2.0 API authentication
Access Controls
Role-based access (RBAC); principle of least privilege enforced
Audit Logging
Complete audit trail; 12-month log retention per VillageReach policy
Incident Response
24-hour breach notification; documented response plan
Compliance
Malawi Data Protection Act (2024); GDPR best practices; VillageReach governance

## Slide 12
Risk Register & Mitigation
Risk
Likelihood
Impact
Mitigation
USSD Gateway Downtime
Medium
High
Dual-network redundancy; proactive monitoring
Low UAT Participation
Low
Medium
Pre-recruit 30 participants; airtime incentives
Chichewa Content Ambiguity
Medium
Medium
Local language specialist; community review
Data Pipeline Delays
Low
High
API-first design; mock endpoints; integration testing Week 2
Scope Creep
Medium
Medium
Change request process; MWK 60,000/hr out-of-scope
Key Personnel Unavailability
Low
High
Cross-trained team; documented handover; 48-hr coverage

## Slide 13
Terms & Conditions
Payment Terms
• Currency: USD (MWK equivalent at prevailing rate)
• Schedule: 40% signing → 20% go-live → 40% monthly
• Payment window: Net 30 days from invoice
• Invoicing: Monthly with time sheets & completion certs
Intellectual Property
• All code & documentation become VillageReach property
• LSH retains proprietary framework rights
• Open-source components under their respective licenses
Confidentiality & Termination
• All project data treated as strictly confidential
• 30-day written notice for termination
• Completed work delivered upon termination
This proposal is valid for 30 days from date of submission.

## Slide 14
Next Steps
1
Proposal Review
VillageReach evaluates technical approach and financial proposal
2
Clarification Meeting
Address questions; align on scope, timeline, and expectations
3
Contract Negotiation
Finalize terms, payment schedule, and NDA execution
4
Kick-Off
Phase 1 begins: stakeholder interviews and wireframe development

## Slide 15
Thank You
Light Speed Holdings
Committed to the success of the CHOICE Project and the communities it serves.
info@lightspeedholdings.com | lightspeedholdings.com
Malawi · Nairobi · Washington DC
Confidential – Prepared for VillageReach CHOICE Project Evaluation